## Sheet1
APPENDIX A: TEMPLATE FOR CLAS INCLUSIVE EXCELLENCE STRATEGIC PLAN FOR UNITS
Unit A's Strategic Plan
Strategic Goal 1. Create a climate to ensure that faculty, staff, and students of every background and identity find purpose, belonging, safety, and opportunities to advance in your unit. (This Goal and the following Objectives intersect with the CLAS Strategic Plan Objectives 1.1, 1.2, 2.5, and 3.2)
Objective | Date objective approved by faculty | Implementation plan | Metrics for success | Timeline | Was objective met? Report date. | Accountability | Example Resources
1. Appoint an EDI Liaison to coordinate EDI activities and climate assessment within the department and meet monthly as a council with AD for Diversity, Outreach, and Initiatives. |  | Ex: 1. The unit Chair will solicit a volunteers at a faculty meeting in October 2022. 2. Candidates will be approved by vote at a subsequent faculty meeting (November 2022). | Ex: Yes/No - Liason Appointed | Ex: 1-3 months (December 2022) |  | Ex: Chairs and directors | UCalifornia Faculty Equity Advisors: https://diversity.berkeley.edu/faculty-equity-advisors; https://inclusion.uci.edu/action-plan/equity-leadership-programs/equity-advisors/
2. Develop a plan to address the climate issues raised in your CWC assessment concerning respect and belonging, communication and transparency, diversity and identities, and job and educational satisfaction and support. | Ex: February 5, 2023 (vote by faculty and staff using an anonymous Qualtrix survey) | Ex: 1. A standing or ad hoc departmental committee will review CWC assessment data. 2. The committee will present the data to the unit faculty and staff at a faculty and staff meeting in December 2022. 3. The committee will compose a plan to address issues specific to the unit using best practices and available resources. 4. The unit faculty and staff will have the opportunity to provide feedback on the plan (Janurary to Februrary 2023). 5. The final draft of the plan will be approved by unit faculty and staff using a March 2023 anonymous Qualtrix survey. | Ex: Yes/No - A written plan to address climate issues specific to the unit that is approved by unit faculty and staff. Ex 2: An increase in climate survey metrics (conducted every 4 years). | Ex: 4-5 months (Spring 2023) |  | Ex: Chairs and directors | Equity-minded faculty workloads: https://advance.umd.edu/node/216; https://www.acenet.edu/Documents/Equity-Minded-Faculty-Workloads-Worksheet-Booklet.pdf; Department Climate: https://provost.columbia.edu/content/guide-best-practices-departmental-climate
2a. Create programming and professional development training that address the ways your disciplines and fields have been complicit in shaping and maintaining racism, colonialism, sexism, homophobia, ableism, and other forms of oppression. |  | Ex: 1. Chair will solict faculty, staff, and student volunteers to form an ad hoc committee or a standing committee (September 2023). 2. Committee will be charged with providing ideas to faculty, students, and staff in Janurary 2024. 3. A vote will be taken using a Qualitrix survey to prioritize the most valued ideas (March 2024). 5. Programming will begin in September 2024. | Ex 1: Yes/No - Programming was conducted. Ex 2: An increase in climate survey metrics (conducted every 4 years). | Ex: 7 years (September 2024 to May 2030). |  | Ex: Chairs and directors | How do disciplinary hierarchies value certain kinds of research over others? And how do these values encourage or discourage EDI research? See p. 26 In https://lsa.umich.edu/content/dam/lsa-site-assets/documents/dei-documents/LSA_DEI_Strategic_Plan_July2020-final.pdf
2b. Establish policies that invite staff, faculty, and students to raise concerns about their learning and working environments without retaliation; and practices that support staff, faculty, and students who are targeted because of their identities and/or teaching or research areas. |  | Ex: 1. The chair/director, in consultation with the unit's DEI liason, faculty (during faculty meeting), staff (staff meetings), and students (in focus groups) will create an anonymous reporting tool using a constantly available Qualtrix survey. 2. The chair/director will monitor the survey for submissions weekly. 3. Submissions will be addressed as they arise by the chair/director in consultation with the appropriate Associate Dean or other relevant representatives. 4. The chair/director will report each semester to all parties how a submitted complaint was addressed without giving private details. 5. The chair/director will consider changes to policies or procedures that place barriers in front of faculty, staff, and students. | Ex: Yes/No - 1. Anonymous reporting tool as created. 2. Chair/director has recorded weekly monitoring of reports. 3. Policies and procedures were altered, if necessary. Ex 2: An increase in climate survey metrics (conducted every 4 years). | 7 years (September 2024 to May 2030). |  | Ex: Chairs and directors | Improving Department Climate: Tools and Resources for Departments and Department Chairs (Columbia), https://fas.columbia.edu/improving-department-climate-tools-and-resources-departments-and-department-chairs
2c. Review and improve department procedures, such as how meetings are conducted and how grievances and complaints are handled, so all people are seen and historically-silenced voices are heard. |  | Ex 1: A version of Robert's Rules of Order are approved by faculty and staff and used consistently in meetings to provide a meeting structure that allows all to contribute comfortably. Ex 2: An anonymous voting tool is created so that any faculty or staff member can call for an anonymous vote on any issue (ex: sli.do). Ex 3: All issues, policies, or proposals on which faculty or staff vote should be presented at least 1 week in advance of the meeting holding the vote. Ex 4: A policy is created for faculty and staff to propose new policies or procedures. | Ex: Yes/No - Unit procedures were reviewed and relevant changes were made. These changes were formally approved as part of revised unit by-laws. Ex 2: An increase in climate survey metrics (conducted every 4 years). | Ex: 4 years (March 2023 to May 2027) |  | Ex: Chairs and directors Ex: Standing and ad hoc committee chairs | Improving Department Climate: Tools and Resources for Departments and Department Chairs (Columbia), https://fas.columbia.edu/improving-department-climate-tools-and-resources-departments-and-department-chairs
Strategic Goal 2. Remove inequities in courses, curricula, and teaching environments so that students of every background and identity have the opportunity to succeed. (CLAS Objectives 1.1, 1.3, and 2.3)
Objective | Date objective approved by faculty | Implementation plan | Metrics for success | Timeline |  | Accountability | Example Resources
1. After your data assessment, provide equity dashboards for all instructional faculty and disseminate those data, for example related to DFW rates and equity-gaps, and use those data to revise curricular policies with a goal of reducing equity gaps and DFW rates. |  | Ex 1: All instructors are provided with a Tableau dashboard so that each can track their equity gaps. Ex 2: The unit will create a standing committee to explore best practices in teaching to evaluate unit data (ex: DFW rates) and propose new policies to the full faculty. Ex 3: All instructors in the unit will be required to - and rewarded for - participate in CU Denver's Inclusive Pedagogy Academy. Ex 4: The chair/director will report to all majors overall DFW rates and the average equity-gap in the unit's courses using a Canvas shell into which all majors are automatically enrolled. This is an effort to provide transparency and accountability. | Ex 1: The average DFW rate os all students declines by 15%. Ex 2: The unit mean equity gap (DFW rate for non-URM students - DFW rate for URM students) will decrease by 25%. Ex 3: >75% of instructors completed the Inclusive Pedagogy Academy. | December 2023 - 2030 |  |  | See U of Wisconsin Milwaukee’s use of DFW dashboards: https://uwm.edu/academicaffairs/student-success/data-of-the-week-dfw-rates/; McNair et al.: Chapter 3 in From Equity Talk to Equity Walk (e-book at Auraria Library)
2. Develop strategies to widely adopt inclusive pedagogical practices, actively using the resources of the Inclusive Pedagogy Academy and the Student Experience Project. |  | Ex: The unit will create a standing committee to explore best practices in teaching to evaluate unit data (ex: DFW rates) and propose new policies to the full faculty. This "Teaching Effectiveness Committee" will also disseminate best practices to all instructors. | Ex 1: The average DFW rate os all students declines by 15%. Ex 2: The unit mean equity gap (DFW rate for non-URM students - DFW rate for URM students) will decrease by 25%. Ex 3: >75% of instructors completed the Inclusive Pedagogy Academy. |  |  |  | Becoming an AntiRacist Educator: https://wheatoncollege.edu/academics/special-projects-initiatives/center-for-collaborative-teaching-and-learning/anti-racist-educator/; Student Experience Project: https://studentexperienceproject.org/; UChicago Inclusive Pedagogy: https://inclusivepedagogy.uchicago.edu/diversity-and-pedagogy; Georgetown Inclusive Pedagogy Toolkit: https://cndls.georgetown.edu/ip-toolkit/; Columbia Guide for Inclusive Teaching: https://ctl.columbia.edu/resources-and-technology/resources/inclusive-teaching-guide/
3. Review department curricular policies to identify whether there are barriers to student success including policies that were informed by deficit thinking (for example, renegotiation of transfer credits, structure of prerequisites). |  | Ex: A standing "Curriculum Committee" will be created in order to strategically analyze the unit's undergraduate and graduate curricula. The committee will propose changes in the structure of majors to the full faculty for a vote. | Ex 1: The average DFW rate os all students declines by 15%. Ex 2: The unit mean equity gap (DFW rate for non-URM students - DFW rate for URM students) will decrease by 25%. Ex 3: Student surveys report an increase in student satisfaction rates. Ex 4: Student retention rates increase by 10% from year 1 to year 2. Ex 5: Graduate rates increase by 10%. |  |  |  | EDI strategic planning toolkit includes a EDI curriculum map on pages 39-40, which asks academic units to assess EDI efforts on a number of levels: 1) Offering courses with multicultural or other diversity-related themes, 2) Ensuring that all students have equitable access to lab groups, study groups, and project teams, 3) Running summer pipeline programs for students from underrepresented communities, 4) Incorporating internships, action research, community projects, or other public-engagement efforts into the curriculum, 5) Using culturally responsive and inclusive teaching strategies, 6) Developing pedagogical approaches that meet the needs of students with disabilities, students with different learning styles, and other targeted populations. Units can use this map to self-assess the multiple ways they are deepening and expanding EDI in their curriculum and pedagogy.
4. Review department curricula to ensure they are antiracist, inclusive, representative of diverse perspectives, methods, and identities. |  | Ex: The unit will create a standing committee to explore best practices in teaching to evaluate unit data (ex: DFW rates) and propose new policies to the full faculty. This "Teaching Effectiveness Committee" will also disseminate best practices to all instructors. | Ex: Yes/No - A review of all syllabi was conducted. Ex: A 25% decrease in student, faculty, and staff complaints as measured in the unit's anonymous reporting tool (Goal 1 - Objective 2b). |  |  |  | Strategies for Antiracist and Decolonized Teaching: Becoming an AntiRacist Educator: https://www.facultyfocus.com/articles/equality-inclusion-and-diversity/strategies-for-antiracist-and-decolonized-teaching/; https://wheatoncollege.edu/academics/special-projects-initiatives/center-for-collaborative-teaching-and-learning/anti-racist-educator/; Georgetown Inclusive Pedagogy Toolkit: https://cndls.georgetown.edu/ip-toolkit/
Strategic Goal 3. Increase the rates of hiring, promotion, and retention of minoritized faculty and staff. (CLAS Objectives 2.2 and 2.4)
Objective | Date objective approved by faculty | Implementation plan | Metrics for success | Timeline |  | Accountability | Example Resources
1. After analyzing hiring data, develop a departmental hiring plan that utilizes best practices and includes a long-term recruitment plan for how to increase diversity of faculty in future hires. |  | Ex: The unit will hold a faculty and staff retreat and using an outside moderator will create a hiring plan. Resources (best practices) will be assigned reading for all participants. Demographic data of employees will be presented before the meeting. | Ex: An increase in the hiring of faculty that possess identies that diversify the unit's faculty and staff. |  |  |  | Santa Clara Strategies for Hiring Toolkit: https://www.scu.edu/diversity/inclusive-hiring-and-recruitment/strategies-toolkit/; UWashington Scouting: https://www.washington.edu/diversity/faculty-advancement/handbook/scouting/;
2. Develop concrete mentoring strategies for minoritized faculty and staff, and junior and IRC faculty more broadly. |  | Ex 1: Junior faculty will be assigned a senior faculty mentor who is either in the unit or outside of it. Ex 2: The unit will create a standing "Mentoring Committee" to provide continuous mentoring to junior faculty. The members of the committee will be provided training about how best to mentor faculty, especially minoritized faculty. Mentoring will be especially guided by the unit's merit review and RTP criteria but will also involve broader mentoring incluing connecting faculty to other staff or faculty who ma be valuable resources. | Ex 1: An increase in the retention of minoritized faculty in the unit. Ex 2: An increase in the units relevant climate survey data. Ex 3: A decrease in complaints reported to the unit's anonymous reporting tool. |  |  |  | Creating Mentoring Relationships: https://advance.wordpress.ncsu.edu/files/2012/02/Bensimon10.pdf; Mutual Mentoring Guide & Grants at UMASS: https://senate.ucsc.edu/committees/cca-committee-on-career-advising/faculty-career-resources/10.-mutual-network-mentoring-guide,-university-of-massachusetts,-amherst.pdf; Mentoring Essays by Rockquemore: See CU Denver's access to NCFDD resources.
3. Develop strategies for collaborative interdisciplinary cluster hires across departments. |  | Ex 1: The unit will collaborate with other units annually (as part of updating a unit's hiring plan) to include at least one hiring priority that is part of a broader, collaborative hiring effort with other units. Ex 2: The unit will form collaborations with members of other units using existing events such as CLAS' Interdisciplinary Exchange to build bridges and organically form collaborative ideas for hiring. Ex 3: The unit will include this objective as part of their broader strategic planning and hiring planning process (Goal 2, Objective 1). | Ex 1: Yes/No - The chair/director can report this occurred annualy. Ex 2: An increase in faculty diversity as reported in unit-specific demographic data. |  |  |  | Berkeley Life Sciences Cluster Hire Initiative: https://ofew.berkeley.edu/sites/default/files/life_sciences_inititatve.year_end_report_summary.pdf; Models for cluster hires: https://www.chronicle.com/article/the-case-for-cluster-hiring-to-diversify-your-faculty/?cid2=gen_login_refresh&cid=gen_sign_in&cid2=gen_login_refresh; Cluster hiring focused on antiracism: https://myusf.usfca.edu/adei/policy-advisement/diverse-faculty-hiring-policy
4. Create policies for transparency around faculty and staff retention offers and salary equity practices. |  | Ex 1: The chair/director will create an ongoing agenda item for faculty and staff meetings to legally allowable details about such efforts in the unit. | Ex 1: Relevant climate data will improve over the timeline. Ex 2: A decrease in complaints reported to the unit's anonymous reporting tool. |  |  |  | Please see p. 27 of U of Michigan's LSA Strategic Plan for ideas regarding retention offers and transparency: https://lsa.umich.edu/content/dam/lsa-site-assets/documents/dei-documents/LSA_DEI_Strategic_Plan_July2020-final.pdf
Strategic Goal 4. Create RTP, merit, and performance review processes and criteria to reward equity, diversity, and inclusion in professional activities. (CLAS Objectives 1.1, 2.2, and 2.4)
Objective | Date objective approved by faculty | Implementation plan | Metrics for success | Timeline |  | Accountability | Example Resources
1. Revise criteria for faculty and staff evaluation, merit, reappointment, tenure, and promotion criteria to recognize and reward significant contributions to diversity, equity, and inclusion in the areas of research, teaching, and service. |  | Ex 1: A standing "Faculty and Staff Evaluation Committee" will be formed and populated by staff, senior and junior faculty. The committee will review existing review criteria (ex: merit review or RTP) and propose new policies and procedures that enure unit-level criteria or contractual obligations are followed in the most transparent fashion. Ex 2: New criteria will be added to policies that specifically reward these efforts instead of burying them into more generial "service" categories. Ex 3: The chair/director will apply unit resources to reward particularly impactful efforts (ex: a teaching release; a transparently advertised 3% additional raise as part of merit review or staff evaluaion. Ex 3: The chair/director will provide professional development funds to reward staff and faculty that made particularly impactful efforts. | Ex 1: An overall increased rate of staff and faculty retention. Ex 2: Increased retention of minoritized faculty and staff. Ex 3: An increase in tenure and promotion rates for minoritized faculty. Ex 4: An increase in professional development acheivements for staff. Ex 5: An increase in relevant climate survey data. |  |  |  | IUPUI Integrated DEI Case for Tenure: https://www.insidehighered.com/news/2021/05/14/iupui-creates-path-promotion-and-tenure-based-dei-work; IUPUI Criteria: https://academicaffairs.iupui.edu/AAContent/Html/Media/AAContent/02-PromotionTenure/PromotionAndTenure/circular-background-description-integrative-dei-case-for-IFC_3_12.pdf; UOregon DEI Statements: https://inclusion.uoregon.edu/content/equity-and-inclusion-personal-statements-reviews-bargaining-unit-faculty; UOregon DEI Requirement for RTP: https://inclusion.uoregon.edu/content/faculty-equity-statements-tenure-promotion-and-review
2. Identify barriers to re-appointment, promotion, and raises in department policies and revise policies accordingly. |  | Ex 1: The relvant standing committee will survey faculty and staff in an anonymous fashion to identify important barriers according to the relevant audience. These data will inform the creation of new policies and procedures and revision of evaluation criteria to obviosly reduce the barriers (ex: how student evaluation data are used in merit review for Senior Instructors). During faculty and staff meetings - or retreats - an outside moderator will be employed to facilitate a discussion of revised policies and procedures faculty and staff would like to emply. |  |  |  |  | Kimberly A. Griffin, "Institutional Barriers, Strategies, and Benefits to Increasing the Representation of Women and Men of Color in the Professoriate," https://diversity.ucdavis.edu/sites/g/files/dgvnsk731/files/inline-files/InstitutionalBarriersStrategies2020.pdf, esp. pp.298-338
3. Fully incorporate interdisciplinary and community-based research and creative work into RTP and merit evaluations. |  | Ex 1: Evaluation criteria (ex: RTP and merit criteria) will be revised to specifically reward these efforts. Ex 2: The chair/director will locate funding to financially support these efforts (ex: through increased gift account donations, partnerships with governmental agencies, and through grant writing. | Ex 1: A document increase in such efforts, collected by the "Evaluation Committee" or the chair/director. Ex 2: An increase in relevant climate survey data. Ex 3: An increase in faculty and staff in general, and more specifically an increase for minoritized unt members. |  |  |  | American University's RTP Diversity Strategic Plan includes questions and recommendations related to EDI community-based research and cross-disciplinary EDI research. https://www.american.edu/provost/academicaffairs/upload/tpr-update_5_scholarship.pdf
Overview and Suggestions:
-Much of the work of strategic planning has been completed for you. Your unit should not have to reinvent the wheel. The table below is a template that can be used by your unit to create an Inclusive Excellence Strategic Plan that meets the specific needs of your unit. Although you can agree to add additional objectives, all of the included objectives should be part of your unit plan. Additional objectives can simply be added to this spreadsheet and then submitted to the CLAS Dean's Office after your unit approves them.
-Please consider that this is a process. It is up to your unit to create your own implementation plans, metrics, and timelines. Others will not "tell" you what to do. You have agency and should take advantage of that to create a plan that matches the aspirations of your unit. Be ambitious and look forward rather than using valuable time complaining about previous experiences. And, remember that the examples provided in the table are just that, examples you can use to start the process. If the unit would like to use the examples, it should. But, each unit should customize their strategic plan to their unit's aspirations.
-Units should be realistic about timelines and metrics used to guage success at meeting objectives. The examples in the table are just that, examples. The provided examples may not reflect unit priorities and should be modified.
-The collection of baseline data as metrics will allow you to assess where your unit has more serious issues. The related objectives can be prioritized in your timeline.
-Metrics that are collected later are critical to measuring if your objectives were met. A metric collected in year 0 or 1 will be provide a baseline measurement as you collect data again in the future. Be specific about your metrics and report how and when you will collect data. Examples have been provided below as a start.
-This strategic planning process also recognizes that much hard work has been accomplished by units. If objectives are underway already, a unit should simply report when it began under the "Date Approved by Faculty" column. If an effort to address an objective began in 2019, please report that but do include a reasonable timeline.
-Climate data will be provided by the CLAS Dean's Office. Climate surveys will be conducted every four years. Equity gap data can be found using the Tableu dashboard provided by Institutional Research.
-A thorough database of published resources and best practices has been provided to you here and at the end of the main plan.
-The creation of your strategic plan should be a collaborative effort and should not be an effort by one or two faculty members, especially if those faculty have identies that place them out of the majority in your unit. Importantly, it is not the role of your DEI Liason to be responsible for taking on most of the burden of this process or, necessarily, even to lead the process. Their main effort should be to connect your efforts with others in CLAS and CU Denver and report to the faculty and staff.
-A unit could consider finding an external facilitator to moderate meetings in order to catalyze the conversation in a productive manner and avoid pitfalls inherent to discussing and utilizing evidence showing deficits in equity in the unit. The facilitator will also ensure that all voices contribute and that a few, the cynical of us included, do not dominate the conversation.
Your unit's strategic plan should be approved by your unit's members according to your by-laws. We encourage these plans to be inclusive as possible.
-A unit should work to approach this project with enthusiasm and, hopfully, with a lack of cynicism.
-And we should all see these plans as "living documents" that should be reviewed at least annually. Progress should regularly be reported to faculty, staff, students, and the CLAS Dean's Office.